## Overzicht per umc
Telemonitoring zwangeren | UMCU | [11 empty] | LUMC | [11 empty] | Radboudumc | [11 empty] | UMCG | [11 empty] | MUMC+ | [11 empty] | AMC | [11 empty] | VUMC | [11 empty] | Erasmus MC | [12 empty] | Legenda
Doelen | 2019 |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  | 2019 |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  | 2019 |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  | 2019 |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  | 2019 |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  | 2019 |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  | 2019 |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  | 2019 |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  | √ | afgerond
| Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 |  | op schema
Stakeholder analyse en draagvlak | [97 empty] | achter op schema | bar: 2019 Q3 to 2022 Q2; 2020 Q3 to 2022 Q2; 2019 Q4 to 2021 Q4; 2019 Q4 to 2022 Q2; 2020 Q3 to 2022 Q2
Multidisciplinair projectteam | [97 empty] | uit fase | bar: 2019 Q3 to 2022 Q2; 2020 Q3 to 2022 Q2; 2019 Q4 to 2021 Q4; 2020 Q2 to 2022 Q2; 2020 Q3 to 2022 Q2; 2020 Q4 to 2022 Q2; 2020 Q3 to 2022 Q2
Nulmeting (cijfers uptake - zie definitie) | [97 empty] | niet van toepassing | bar: 2019 Q3 to 2022 Q2; 2020 Q3 to 2022 Q2; 2021 Q2 to 2021 Q4; 2020 Q2 to 2022 Q2; 2021 Q2 to 2022 Q2
Workflow omschrijving huidige proces | [97 empty] | staat gepland | bar: 2019 Q3 to 2022 Q2; 2020 Q4 to 2022 Q2; 2021 Q2 to 2021 Q4; 2020 Q2 to 2022 Q2; 2020 Q4 to 2022 Q2; 2021 Q1 to 2022 Q2; 2020 Q4 to 2022 Q2
Voorbereiding gesprekken koppeling EPD | [97 empty] | volgt in de toekomst | bar: 2019 Q3 to 2022 Q2; 2020 Q4 to 2022 Q2; 2020 Q3; 2021 Q3 to 2021 Q4; 2020 Q2 to 2022 Q2; 2020 Q3 to 2022 Q2; 2020 Q4 to 2022 Q2; 2020 Q4 to 2022 Q2
Verkenning (en zo mogelijk afspraken) leveranciers | [97 empty] | umc waar het project gestart is tijdens Citrien-1 | bar: 2019 Q3 to 2022 Q2; 2020 Q4 to 2022 Q2; 2020 Q3 to 2021 Q4; 2020 Q2 to 2022 Q2; 2020 Q4 to 2022 Q2; 2021 Q1 to 2022 Q2; 2020 Q4 to 2022 Q2
Deelname wetenschappelijk onderzoek verkend | bar: 2019 Q3 to 2022 Q2; 2020 Q2; 2021 Q1 to 2021 Q4; 2020 Q1 to 2021 Q4; 2020 Q2 to 2022 Q2; 2021 Q2 to 2022 Q2; 2021 Q3 to 2022 Q2; 2020 Q3 to 2022 Q2
Inventarisatie resources en middelen (FINANCIEN) | bar: 2019 Q3 to 2022 Q2; 2020 Q2; 2022 Q1 to 2022 Q2; 2020 Q1 to 2021 Q4; 2020 Q2 to 2022 Q2; 2020 Q3; 2021 Q4 to 2022 Q2; 2020 Q2; 2021 Q4 to 2022 Q2; 2021 Q1 to 2022 Q2
Uitwerken beoogd zorgpad & logistiek | bar: 2019 Q3 to 2022 Q2; 2020 Q2; 2022 Q1 to 2022 Q2; 2020 Q4 to 2021 Q4; 2020 Q2 to 2022 Q2; 2021 Q4 to 2022 Q2; 2021 Q4 to 2022 Q2; 2020 Q4 to 2022 Q2
Uitwerken patientinformatie | bar: 2019 Q3 to 2022 Q2; 2020 Q4 to 2022 Q2; 2020 Q4 to 2021 Q4; 2020 Q3 to 2022 Q2; 2020 Q4; 2021 Q2; 2021 Q4 to 2022 Q2; 2021 Q2; 2021 Q4 to 2022 Q2; 2020 Q4 to 2022 Q2
Voorlichten professionals | bar: 2019 Q3 to 2022 Q2; 2021 Q4 to 2022 Q2; 2020 Q4 to 2021 Q4; 2020 Q3 to 2022 Q2; 2020 Q4; 2021 Q2; 2020 Q4; 2021 Q2; 2020 Q4 to 2022 Q2
Werkinstructies protocollen op stellen | bar: 2019 Q3 to 2022 Q2; 2021 Q4 to 2022 Q2; 2020 Q4 to 2021 Q4; 2020 Q2 to 2022 Q2; 2020 Q4; 2021 Q2; 2020 Q4; 2021 Q2; 2020 Q4 to 2022 Q2
Indien deelname wetenschappelijk onderzoek: voorbereiden | bar: 2019 Q3 to 2019 Q4; 2022 Q1 to 2022 Q2; 2020 Q2; 2021 Q1 to 2021 Q4; 2020 Q4 to 2021 Q4; 2020 Q2 to 2022 Q2; 2020 Q3 to 2020 Q4; 2021 Q2 to 2022 Q2; 2020 Q3 to 2020 Q4; 2021 Q2 to 2022 Q2; 2020 Q4 to 2022 Q2
Infrastructuur ICT en EPD wordt aangepast om een view in EPD te hebben | bar: 2019 Q3 to 2022 Q2; 2020 Q4 to 2022 Q2; 2020 Q4 to 2021 Q4; 2021 Q2 to 2022 Q2; 2020 Q2; 2020 Q4; 2021 Q4 to 2022 Q2; 2020 Q2; 2020 Q4 to 2021 Q2; 2021 Q4 to 2022 Q2; 2020 Q4 to 2022 Q2
Projectplanning klaar | bar: 2019 Q3 to 2022 Q2; 2020 Q3 to 2022 Q2; 2020 Q4 to 2021 Q4; 2020 Q4 to 2022 Q2; 2020 Q2; 2020 Q2; 2020 Q3 to 2022 Q2
Studie uitvoeren | bar: 2019 Q3 to 2022 Q2; 2020 Q2; 2021 Q1 to 2021 Q4; 2021 Q2 to 2021 Q4; 2021 Q1 to 2022 Q2; 2020 Q2 to 2020 Q4; 2021 Q2 to 2022 Q2; 2020 Q2 to 2020 Q4; 2021 Q2 to 2022 Q2; 2020 Q3; 2021 Q1 to 2022 Q2
Contact leggen met perifeer ziekenhuis (UMCG_OZG) | bar: 2019 Q3 to 2022 Q2; 2020 Q2 to 2020 Q3; 2021 Q2 to 2021 Q3; 2022 Q2; 2020 Q2; 2021 Q2 to 2022 Q2; 2021 Q1 to 2022 Q2; 2021 Q1 to 2022 Q2
Afspraken inkoop | bar: 2019 Q3 to 2022 Q2; 2020 Q1 to 2022 Q2; 2021 Q2 to 2021 Q4; 2021 Q2 to 2021 Q4; 2020 Q4 to 2021 Q2; 2020 Q4 to 2021 Q3; 2020 Q4 to 2022 Q2
Start patient inclusie | bar: 2020 Q2 to 2020 Q3; 2020 Q4 to 2022 Q2; 2021 Q1; 2021 Q3 to 2022 Q2
Afspraken zorgverzekeraar | bar: 2019 Q3 to 2022 Q2; 2022 Q2; 2021 Q3 to 2021 Q4; 2020 Q4 to 2021 Q2; 2020 Q4 to 2021 Q3; 2021 Q1 to 2021 Q2
update cijfers opschaling | bar: 2019 Q3 to 2021 Q1; 2022 Q1 to 2022 Q2; 2021 Q3 to 2022 Q2; 2021 Q4; 2021 Q2 to 2021 Q4; 2021 Q2 to 2022 Q2
periodiek overleg projectteam | bar: 2019 Q3 to 2022 Q2; 2021 Q2 to 2022 Q2; 2021 Q1 to 2022 Q2; 2021 Q1 to 2021 Q4; 2021 Q4 to 2022 Q2; 2021 Q4 to 2022 Q2; 2021 Q1 to 2022 Q2
Start patient inclusie | bar: 2019 Q3 to 2022 Q2; 2021 Q1 to 2022 Q2; 2021 Q1 to 2021 Q4; 2021 Q2 to 2021 Q4; 2021 Q2; 2021 Q1 to 2021 Q4; 2021 Q1 to 2022 Q2
PRI uitgevoerd | bar: 2019 Q3 to 2022 Q2; 2021 Q1 to 2021 Q4; 2021 Q4 to 2022 Q2; 2021 Q1 to 2021 Q2; 2021 Q4 to 2022 Q2; 2021 Q1 to 2022 Q2
Logistiek proces vastgesteld | bar: 2019 Q3 to 2022 Q2; 2021 Q1 to 2021 Q4; 2021 Q4 to 2022 Q2; 2021 Q1 to 2021 Q2; 2021 Q4 to 2022 Q2; 2021 Q1 to 2022 Q2
Evaluatie | bar: 2019 Q3 to 2022 Q2; 2021 Q1 to 2021 Q4; 2021 Q1 to 2021 Q4; 2020 Q4 to 2021 Q2; 2021 Q4 to 2022 Q2
Patienteninformatie en proces juridisch getoetst | bar: 2019 Q3 to 2022 Q2; 2021 Q1 to 2021 Q4; 2021 Q4 to 2022 Q2; 2021 Q1 to 2021 Q2; 2021 Q4 to 2022 Q2; 2021 Q1 to 2022 Q2
Note on BN6: H.J.H. Gijsbers: nu cijfers doelgroep verzameld. Nog geen inclusies geweest. Vragenlijst was al uitgezet
Note on BM7: H.J.H. Gijsbers besproken met onderzoeker UMCU. Mogelijk in klinisch thuismonitoring team
Note on BN7: H.J.H. Gijsbers: is al wel besproken, maar moet verder uitgewerkt worden als technisch alles werkt.
Note on BM8: H.J.H. Gijsbers: projectvoorstel bij afdeling EPIC. Analsye door informatiemanager
Note on BM9: H.J.H. Gijsbers: gaat nu starten
Note on BM10: H.J.H. Gijsbers: GYN wil graag deelnemen aan safe@home studie
Note on BQ10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Deelname is wel verkend. GYN willen ook deelnemen. Het werkt nog niet in EPIC en de vraag is of AmsterdamUMC alle data kan aanleveren aan de onderzoekers.
Note on BS10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Deelname blijft onzeker. We hopen dat in Q4 de toepassing kan starten, maar we zijn al erg laat.
Note on BT10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Deelname blijft onzeker. We hopen dat in Q4 de toepassing kan starten, maar we zijn al erg laat.
Note on BU10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Deelname blijft onzeker. Door vertraging al niet mogelijk geweest. Nu start in april maar onvolledig volgens norm van safe@home
Note on CE10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Deelname blijft onzeker. We hopen dat in Q4 de toepassing kan starten, maar we zijn al erg laat.
Note on CF10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Deelname blijft onzeker. We hopen dat in Q4 de toepassing kan starten, maar we zijn al erg laat.
Note on CG10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Deelname blijft onzeker.
Note on AH11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: interne innovatiesubsidie
Note on BN11: H.J.H. Gijsbers: nog onduidelijkheid over licentiekosten. Best veel voor 18 maanden
Note on BP11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: inmiddels keuze voor EPIC gemaakt. Daarmee ook andere kosten en tijdsinvestering nodig. Nog niet afgerond
Note on BT14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In januari de zorgverleners inwerken op EPIC.
Note on BU14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In januari was gepland zorgverleners in te werken op EPIC. Dit wordt nu maart.
Note on CF14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In januari de zorgverleners inwerken op EPIC.
Note on CG14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In januari de zorgverleners inwerken op EPIC.
Note on AE15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: voor de pilot gereed
Note on BN16: H.J.H. Gijsbers: Keuze voor techniek lijkt nu ook de keuze voor start deelname onderzoek.
Note on BP17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Keuze voor EPIC, dus geen view meer nodig naar LUscii
Note on CB17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Keuze voor EPIC, dus geen view meer nodig naar LUscii
Note on BP19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5 februari afspraak met Mireille of dit nog kan Reply: meedoen kan. Dataextractie nog niet mogelijk, dus alles via een gastaanstelling
Note on CB19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5 februari afspraak met Mireille of dit nog kan Reply: meedoen kan. Dataextractie nog niet mogelijk, dus alles via een gastaanstelling
Note on AH23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: interne innovatie subsidie, betaalbaar beter VGZ
Note on BP24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cijfers verder corrigeren voor doelgroep
Note on BT24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dashboard gebouwd
Note on BU24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dashboard gebouwd
Note on CF24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dashboard gebouwd
Note on CG24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dashboard gebouwd

## Legenda
Legenda
√ | afgerond
op schema
achter op schema
uit fase
niet van toepassing
staat gepland
volgt in de toekomst
umc waar het project gestart is tijdens Citrien-1

## Definities begrippen
Begrippen | Definities :
Stakeholder analyse en commitment: | Inzicht in betrokken partijen, hun rol, invloed en wensen.
Multidisciplinair projectteam: | Het uitvoerend projectteam. Dit is het projectteam, aangevuld met bijv. direct betrokken artsen, verpleegkundigen, ICT’ers, etc.
Workflow analyse van het huidige proces/zorgpad: | Analyse van de huidige werkwijze rondom het betreffende zorgpad / het betreffende concept.
Nulmeting: | Hoe groot is de patiëntpopulatie die het nieuwe zorgconcept reeds ontvangt? Hoe groot is de patiëntpopulatie is die in aanmerking zou kunnen komen voor het nieuwe zorgpad.
Werkinstructies/protocollen opstellen | Benodigde protocollen opstellen voor nieuwe werkwijze bij bijbehorend nieuw / aangepast zorgpad n.a.v. het concept dat wordt geïmplementeerd.

## kopie (versie april)
| UMCU |  |  |  |  | LUMC |  |  |  |  | Radboudumc |  |  |  |  | UMCG |  |  |  |  | MUMC+ |  |  |  |  | AMC |  |  |  |  | VUMC |  |  |  |  | ErasmusMC | [5 empty] | Legenda
Doelen | 2019 |  | 2020 |  |  | 2019 |  | 2020 |  |  | 2019 |  | 2020 |  |  | 2019 |  | 2020 |  |  | 2019 |  | 2020 |  |  | 2019 |  | 2020 |  |  | 2019 |  | 2020 |  |  | 2019 |  | 2020 |  |  | √ | afgerond
| Q3 | Q4 | Q1 | Q2 | Q3 | Q3 | Q4 | Q1 | Q2 | Q3 | Q3 | Q4 | Q1 | Q2 | Q3 | Q3 | Q4 | Q1 | Q2 | Q3 | Q3 | Q4 | Q1 | Q2 | Q3 | Q3 | Q4 | Q1 | Q2 | Q3 | Q3 | Q4 | Q1 | Q2 | Q3 | Q3 | Q4 | Q1 | Q2 | Q3 |  | op schema
Stakeholder analyse en draagvlak | √ | √ | √ | √ | √ | √ | √ | [9 empty] | √ | √ | √ | √ |  | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | [6 empty] | achter op schema
Multidisciplinair projectteam | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | [13 empty] | √ | √ | [16 empty] | uit fase
Nulmeting (cijfers uptake - zie definitie) | √ | √ | √ | √ | √ | [12 empty] | √ | √ | √ |  |  |  | √ | √ | [16 empty] | niet van toepassing
Workflow omschrijving huidige proces | √ | √ | √ | √ | √ |  | √ | √ | √ | √ | [13 empty] | √ | √ | [16 empty] | toekomstige planning
Voorbereiding gesprekken koppeling EPD | √ | √ | √ | √ | √ | [18 empty] | √ | √ | [16 empty] | umc waar het project gestart is tijdens Citrien-1
Verkenning (en zo mogelijk afspraken) leveranciers | √ | √ | √ | √ | √ |  | √ | √ | [15 empty] | √ | √
Deelname wetenschappelijk onderzoek verkend | √ | √ | √ | √ | √ |  |  | √ | [10 empty] | √ |  |  |  |  | √ | √
Inventarisatie resources en middelen
Uitwerken beoogd zorgpad & logistiek
Onderzoek naar benodigde inhoud Box | [7 empty] | √ | √
LUMC Box generieke processen uitwerken
Uitwerken patientinformatie
Voorlichten professionals
Werkinstructies protocollen op stellen
Indien deelname wetenschappelijk onderzoek: voorbereiden
Infrastructuur ICT en EPD wordt aangepast om een view in EPD te hebben
Projectplanning klaar
Studie uitvoeren
Afspraak inkoop en zorgverzekeraar
Start patient inclusie